## myfile
|  |  |  | TASK | START DATE | DURATION
WP1 | Management & Coordination | 2022-09-01 | 2026-08-31 | WP1. Management & Coordination | 2022-09-01 | 1460
WP1 | M1.1 Kick-off of ET-PP coordination | 2022-09-30 | 2022-10-01 | M1.1 Kick-off of ET-PP coordination | 2022-09-30 | 1
WP1 | M1.2 ET-PP first year internal review | 2023-08-31 | 2023-09-01 | M1.2 ET-PP first year internal review | 2023-08-31 | 1
WP1 | D1.1 First report to EC | 2024-02-29 | 2024-03-01 | D1.1 First report to EC | 2024-02-29 | 1
WP1 | M1.3 ET-PP middle term internal review | 2024-08-31 | 2024-09-01 | M1.3 ET-PP middle term internal review | 2024-08-31 | 1
WP1 | D1.2 Second Report to EC | 2025-08-30 | 2025-08-31 | D1.2 Second Report to EC | 2025-08-30 | 1
WP1 | M1.4 ET-PP final internal review | 2026-05-31 | 2026-06-01 | M1.4 ET-PP final internal review | 2026-05-31 | 1
WP1 | D1.3 Final Report to EC | 2026-08-30 | 2026-08-31 | D1.3 Final Report to EC | 2026-08-30 | 1
WP2 | WP2. Organization, Governance and Legal Aspects | 2022-09-01 | 2026-08-31 | WP2. Organization, Governance and Legal Aspects | 2022-09-01 | 1460
| D2.1 Kick-off meeting | 2022-09-30 | 2022-10-01 | D2.1 Kick-off meeting | 2022-09-30 | 1
| D2.2 Report providing options for legal entity | 2023-08-31 | 2023-09-01 | D2.2 Report providing options for legal entity | 2023-08-31 | 1
| D2.3 Minutes of meetings with EC and involved ministries | 2023-08-31 | 2023-09-01 | D2.3 Minutes of meetings with EC and involved ministries | 2023-08-31 | 1
| D2.4 Legal documents and statutes | 2024-08-31 | 2024-09-01 | D2.4 Legal documents and statutes | 2024-08-31 | 1
| D2.5 Legal entity statutes | 2025-08-30 | 2025-08-31 | D2.5 Legal entity statutes | 2025-08-30 | 1
| D2.6 Legal entity established | 2026-08-30 | 2026-08-31 | D2.6 Legal entity established | 2026-08-30 | 1
WP3 | WP3. Financial Architecture | 2022-09-01 | 2026-08-31 | WP3. Financial Architecture | 2022-09-01 | 1460
WP3 | M3.1 Constitution / first meeting of the resource board | 2025-05-31 | 2025-06-01 | M3.1 Constitution / first meeting of the resource board | 2025-05-31 | 1
WP3 | D3.1 Handbook for design and construction phase | 2025-08-30 | 2025-08-31 | D3.1 Handbook for design and construction phase | 2025-08-30 | 1
WP3 | D3.2 Handbook for operation phase | 2026-02-28 | 2026-03-01 | D3.2 Handbook for operation phase | 2026-02-28 | 1
WP3 | D3.3 Financial plan and Scenario analysis | 2026-08-30 | 2026-08-31 | D3.3 Financial plan and Scenario analysis | 2026-08-30 | 1
WP4 | WP4. Site Selection Preparation | 2022-09-01 | 2025-08-31 | WP4. Site Selection Preparation | 2022-09-01 | 1095
| M4.1 Document detailing the site-specific characteristics | 2022-12-30 | 2022-12-31 | M4.1 Document detailing the site-specific characteristics | 2022-12-30 | 1
| M4.2 Common methodology to estimate impact of site characteristics on ET sensitivity | 2023-06-30 | 2023-07-01 | M4.2 Common methodology to estimate impact of site characteristics on ET sensitivity | 2023-06-30 | 1
| D4.1 Scan of legal procedures | 2023-06-30 | 2023-07-01 | D4.1 Scan of legal procedures | 2023-06-30 | 1
| D4.2 Updated socio-economic impact studies | 2023-11-30 | 2023-12-01 | D4.2 Updated socio-economic impact studies | 2023-11-30 | 1
| D4.3 Complete quantification of all the aspects impacting the Einstein Telescope performance | 2024-06-30 | 2024-07-01 | D4.3 Complete quantification of all the aspects impacting the Einstein Telescope performance | 2024-06-30 | 1
| D4.4 3D geology, hydrology, etc. model | 2024-12-30 | 2024-12-31 | D4.4 3D geology, hydrology, etc. model | 2024-12-30 | 1
| D4.5 Robust and complete cost and schedule estimates of the excavations | 2025-08-30 | 2025-08-31 | D4.5 Robust and complete cost and schedule estimates of the excavations | 2025-08-30 | 1
WP5 | WP5. Project Office & Engineering Department | 2022-09-01 | 2026-08-31 | WP5. Project Office & Engineering Department | 2022-09-01 | 1460
| M5.1 The recruitment of the Project Office team is completed. | 2023-12-30 | 2023-12-31 | M5.1 The recruitment of the Project Office team is completed. | 2023-12-30 | 1
| D5.1 A document which defines the structure and the mandate of the Project Office. | 2024-09-30 | 2024-10-01 | D5.1 A document which defines the structure and the mandate of the Project Office. | 2024-09-30 | 1
| D5.2 A document describing the functionalities required | 2024-09-30 | 2024-10-01 | D5.2 A document describing the functionalities required | 2024-09-30 | 1
| D5.3 A document containing the structure and the mandate of the Engineering Department. | 2024-09-30 | 2024-10-01 | D5.3 A document containing the structure and the mandate of the Engineering Department. | 2024-09-30 | 1
| M5.2 All documents published | 2024-09-30 | 2024-10-01 | M5.2 All documents published | 2024-09-30 | 1
| M5.3 Engineeting Department completed | 2024-11-30 | 2024-12-01 | M5.3 Engineeting Department completed | 2024-11-30 | 1
| D5.4 The Engineering Department as a functional unit | 2025-01-01 | 2025-01-02 | D5.4 The Engineering Department as a functional unit | 2025-01-01 | 1
| M5.4 Project Office completed | 2024-11-30 | 2024-12-01 | M5.4 Project Office completed | 2024-11-30 | 1
| D5.5 The operational Project Office as a functional unit | 2025-01-01 | 2025-01-02 | D5.5 The operational Project Office as a functional unit | 2025-01-01 | 1
WP6 | WP6. Technical Design | 2022-09-01 | 2026-08-31 | WP6. Technical Design | 2022-09-01 | 1460
| M6.1 ET Collaboration in place | 2023-09-01 | 2023-09-02 | M6.1 ET Collaboration in place | 2023-09-01 | 1
| D6.1 Refined Science Case | 2024-03-01 | 2024-03-02 | D6.1 Refined Science Case | 2024-03-01 | 1
| D6.2 Vacuum pipe Design | 2024-09-01 | 2024-09-02 | D6.2 Vacuum pipe Design | 2024-09-01 | 1
| D6.3 Preliminary RI TDR | 2024-09-01 | 2024-09-02 | D6.3 Preliminary RI TDR | 2024-09-01 | 1
| D6.4 Preliminary DET TDR | 2024-09-01 | 2024-09-02 | D6.4 Preliminary DET TDR | 2024-09-01 | 1
| D6.5 RI TDR | 2026-01-01 | 2026-01-02 | D6.5 RI TDR | 2026-01-01 | 1
| D6.6 DMP and Data Access Policy | 2026-08-30 | 2026-08-31 | D6.6 DMP and Data Access Policy | 2026-08-30 | 1
WP7 | WP7 - Innovation and industry engagement | 2022-09-01 | 2026-05-29 | WP7 - Innovation and industry engagement | 2022-09-01 | 1366
WP7 | WP7.1 - Promotion of innovative technologies | 2022-09-01 | 2023-08-30 | WP7.1 - Promotion of innovative technologies | 2022-09-01 | 363
WP7 | WP7.1.1 - ET innovation objectives | 2022-09-01 | 2023-03-31 | WP7.1.1 - ET innovation objectives | 2022-09-01 | 211
WP7 | M7.1 - Analysis of promotion strategies accomplished | 2023-04-27 | 2023-04-28 | M7.1 - Analysis of promotion strategies accomplished | 2023-04-27 | 1
WP7 | WP7.1.2 - ET innovation plan | 2023-03-31 | 2023-07-31 | WP7.1.2 - ET innovation plan | 2023-03-31 | 122
WP7 | D7.1 - Innovation Plan | 2023-08-29 | 2023-08-30 | D7.1 - Innovation Plan | 2023-08-29 | 1
WP7 | WP7.2 - Liaison with industry | 2022-09-01 | 2026-03-31 | WP7.2 - Liaison with industry | 2022-09-01 | 1307
WP7 | WP7.2.1 - Industrial participation: risks and mitigations | 2022-09-01 | 2023-02-01 | WP7.2.1 - Industrial participation: risks and mitigations | 2022-09-01 | 153
WP7 | WP7.2.2 - Promoting the engagement: the national initiatives | 2022-11-04 | 2023-01-04 | WP7.2.2 - Promoting the engagement: the national initiatives | 2022-11-04 | 61
WP7 | WP7.2.3 - Engagement plan definition | 2023-02-02 | 2023-06-16 | WP7.2.3 - Engagement plan definition | 2023-02-02 | 134
WP7 | M7.2 - Engagement plan produced | 2023-06-29 | 2023-06-30 | M7.2 - Engagement plan produced | 2023-06-29 | 1
WP7 | WP7.2.4 - Engagement plan execution | 2023-06-19 | 2026-02-17 | WP7.2.4 - Engagement plan execution | 2023-06-19 | 974
WP7 | WP7.2.5 - Report on engagement activities | 2026-02-17 | 2026-03-31 | WP7.2.5 - Report on engagement activities | 2026-02-17 | 42
WP7 | D7.2 - Report on industry engagement plan execution | 2026-03-30 | 2026-03-31 | D7.2 - Report on industry engagement plan execution | 2026-03-30 | 1
WP7 | WP7.2.6 - Strategy on Industrial Return | 2023-06-19 | 2023-12-01 | WP7.2.6 - Strategy on Industrial Return | 2023-06-19 | 165
WP7 | M7.3 - Analysis of balanced industrial return strategies accomplished | 2023-12-28 | 2023-12-29 | M7.3 - Analysis of balanced industrial return strategies accomplished | 2023-12-28 | 1
WP7 | WP7.2.7 - Indistrial return implementation model | 2025-01-27 | 2025-04-28 | WP7.2.7 - Indistrial return implementation model | 2025-01-27 | 91
WP7 | D7.3 - Model for pursuing in ET a balanced industrial return | 2025-05-29 | 2025-05-30 | D7.3 - Model for pursuing in ET a balanced industrial return | 2025-05-29 | 1
WP7 | WP7.3 - Technology transfer principles | 2025-06-02 | 2026-05-29 | WP7.3 - Technology transfer principles | 2025-06-02 | 361
WP7 | WP 7.3.1 - Technology transfer principles | 2025-06-02 | 2025-09-19 | WP 7.3.1 - Technology transfer principles | 2025-06-02 | 109
WP7 | WP7.3.2 - Technology trasfer and IP management model | 2025-09-22 | 2026-05-29 | WP7.3.2 - Technology trasfer and IP management model | 2025-09-22 | 249
WP7 | D7.4 - Report on TT and Intellectual property management in ET | 2026-05-28 | 2026-05-29 | D7.4 - Report on TT and Intellectual property management in ET | 2026-05-28 | 1
WP8 | WP8. Computing and data access model | 2022-09-01 | 2026-08-31 | WP8. Computing and data access model | 2022-09-01 | 1460
WP8 | M8.1 Workflows Requirements collection and constraints: computing and data | 2023-09-01 | 2023-09-02 | M8.1 Workflows Requirements collection and constraints: computing and data | 2023-09-01 | 1
WP8 | D8.1 Computing and Data Requirements | 2024-02-01 | 2024-02-02 | D8.1 Computing and Data Requirements | 2024-02-01 | 1
WP8 | M8.2 Computing Infrastructures availability for ET workflows, characteristics | 2024-09-01 | 2024-09-02 | M8.2 Computing Infrastructures availability for ET workflows, characteristics | 2024-09-01 | 1
WP8 | M8.3 On site infrastructure, computing and data model | 2025-09-01 | 2025-09-02 | M8.3 On site infrastructure, computing and data model | 2025-09-01 | 1
WP8 | M8.4 Low latency and offline workflows and computing model | 2025-12-01 | 2025-12-02 | M8.4 Low latency and offline workflows and computing model | 2025-12-01 | 1
WP8 | D8.2 Computing and Data Model | 2026-02-28 | 2026-03-01 | D8.2 Computing and Data Model | 2026-02-28 | 1
WP8 | D8.3 Data Access Implementation Guidelines | 2026-08-30 | 2026-08-31 | D8.3 Data Access Implementation Guidelines | 2026-08-30 | 1
WP8 | M8.5 Data management, access, policy and implementation | 2026-08-30 | 2026-08-31 | M8.5 Data management, access, policy and implementation | 2026-08-30 | 1
WP9 | WP9. Sustainable Development Strategy | 2022-09-01 | 2026-08-31 | WP9. Sustainable Development Strategy | 2022-09-01 | 1460
| D9.1 ET Sustainable Development Implementation Strategy | 2023-08-30 | 2023-08-31 | D9.1 ET Sustainable Development Implementation Strategy | 2023-08-30 | 1
| M9.1 Preliminary sustainability plan | 2023-08-30 | 2023-08-31 | M9.1 Preliminary sustainability plan | 2023-08-30 | 1
| M9.2 Sustainability workshop | 2024-02-29 | 2024-03-01 | M9.2 Sustainability workshop | 2024-02-29 | 1
| D9.2 ET Environmental impact assessment and mitigation strategy | 2024-08-30 | 2024-08-31 | D9.2 ET Environmental impact assessment and mitigation strategy | 2024-08-30 | 1
| D9.3 ET CO2 footprint ET assessment and mitigation strategy | 2025-08-30 | 2025-08-31 | D9.3 ET CO2 footprint ET assessment and mitigation strategy | 2025-08-30 | 1
| M9.3 Final sustainability plan | 2026-08-30 | 2026-08-31 | M9.3 Final sustainability plan | 2026-08-30 | 1
WP10
| WP10. Education, Outreach and Citizen Engagement | 2022-09-01 | 2025-08-31 | WP10. Education, Outreach and Citizen Engagement | 2022-09-01 | 1095
| D10.1 Communications, outreach procedures | 2023-02-28 | 2023-03-01 | D10.1 Communications, outreach procedures | 2023-02-28 | 1
| M10.1 Appointment of COC | 2023-02-28 | 2023-03-01 | M10.1 Appointment of COC | 2023-02-28 | 1
| M10.2 Set up C&O points of contact network | 2023-02-28 | 2023-03-01 | M10.2 Set up C&O points of contact network | 2023-02-28 | 1
| D10.2 Consortium website and social media | 2023-08-30 | 2023-08-31 | D10.2 Consortium website and social media | 2023-08-30 | 1
| M10.3 ET Consortium website and social media launch | 2023-08-30 | 2023-08-31 | M10.3 ET Consortium website and social media launch | 2023-08-30 | 1
| D10.3 Strategic media and communications plan | 2023-08-30 | 2023-08-31 | D10.3 Strategic media and communications plan | 2023-08-30 | 1
| D10.4 Initial bank of graphics, multimedia | 2024-08-30 | 2024-08-31 | D10.4 Initial bank of graphics, multimedia | 2024-08-30 | 1
| D10.5 Strategy for ECR training programme | 2025-08-30 | 2025-08-31 | D10.5 Strategy for ECR training programme | 2025-08-30 | 1
| M10.4 Complete strategy for ECR training programme | 2025-08-30 | 2025-08-31 | M10.4 Complete strategy for ECR training programme | 2025-08-30 | 1