## deliverables
Deliverable (number SYSTEM) | Deliverable (number) | Deliverable name | Work package number | Short name of lead participant | Type | Dissemination level | Delivery date (month
No hay que listarlo | D1.1 | Report to EC | WP1 | IFAE | R | PU | M18
No hay que listarlo | D1.2 | Report to EC | WP1 | IFAE | R | PU | M36
No hay que listarlo | D1.3 | Report to EC | WP1 | IFAE | R | PU | M48
1 |  | Dissemination and Exploitation (D&E) Plan | WP1 | IFAE | R | SEN | M6
2 |  | Data Management Plan (DMP) | WP2 | IFAE | R | SEN | M6
3 | D2.1 | Report providing options for legal entity | WP2 | NIKHEF | R | PU | M12
4 | D2.2 | Minutes of meetings with EC and involved ministries | WP2 | NIKHEF | R | PU | M12
5 | D2.3 | Legal entity statutes | WP2 | NIKHEF | R | PU | M36
6 | D2.4 | Roadmap to establish the legal entity and its implementation. | WP2 | NIKHEF | R | PU | M48
7 | D3.1 | Handbook for design and construction phase | WP3 | UCL | R | PU | M36
8 | D3.2 | Handbook for operating phase | WP3 | UCL | R | PU | M42
9 | D3.3 | Financial plan and Scenario analysis | WP3 | UCL | R, O | PU | M48
10 | D4.1 | Scan of legal procedures, permitting and land acquisitions i.e. the steps to be taken prior to starting excavations. | WP4 | NIKHEF | R | PU | M10
11 | D4.2 | Updated socio-economic impact studies | WP4 | INFN | R | PU | M15
12 | D4.3 | Complete quantification of all the aspects impacting the ET performance. | WP4 | UW | R | PU | M22
13 | D4.4 | 3D geology, hydrology, etc. model with detailed localisation of the ET infrastructure. | WP4 | INFN | R | PU | M27
14 | D4.5 | Robust and complete cost and schedule estimates of the excavations. | WP4 | NIKHEF | R | PU | M36
15 | D5.1 | Structure and mandate of the Project Office | WP5 | CNRS | R | PU | M25
16 | D5.2 | Functionalities required from the tools in support of the project management | WP5 | CNRS | R | PU | M25
17 | D5.3 | Structure and mandate of the Engineering Department | WP5 | CNRS | R | PU | M25
18 | D5.4 | Funcional Engineering Department | WP5 | NIKHEF | R | PU | M28
19 | D5.5 | Funcional Project Office | WP5 | INFN | R | PU | M28
20 | D6.1 | Refined Science Case | WP6 | UNIGE | R | PU | M18
21 | D6.2 | Vacuum pipe Design | WP6 | ANTW | R | PU | M24
22 | D6.3 | Preliminary RI TDR | WP6 | INFN | R | PU | M24
23 | D6.4 | Preliminary DET TDR | WP6 | NIKHEF | R | PU | M24
24 | D6.5 | RI TDR | WP6 | INFN | R | PU | M40
25 | D6.6 | DMP and Data Access Policy | WP6 | DESY | R | PU | M46
26 | D7.1 | Innovation plan | WP7 | IFAE | R | PU | M12
27 | D7.2 | Report on industry engagement plan execution | WP7 | NIKHEF | R | PU | M42
28 | D7.3 | Model for pursuing in ET a balanced industrial return | WP7 | INFN | R | PU | M33
29 | D7.4 | Report on TT and Intellectual property management in ET | WP7 | INFN | R | PU | M44
30 | D8.1 | Computing and Data Requirements | WP8 | UNIGE | R | PU | M18
31 | D8.2 | Computing and Data Model | WP8 | UNIGE | R | PU | M42
32 | D8.3 | Data Access Implementation Guidelines | WP8 | BSC | R | PU | M48
33 | D9.1 | ET Sustainable Development Implementation Strategy | WP9 | CNRS | R | PU | 12
34 | D9.2 | ET Environmental impact assessment and mitigation strategy | WP9 | INFN | R | PU | 24
35 | D9.3 | ET CO2 footprint ET assessment and mitigation strategy | WP9 | EGO | R | PU | 36
36 | D10.1 | Initiate strategic media and communications plan | WP10 | UW | R | PU | 12
37 | D10.2 | Launch consortium website and social media accounts | WP10 | EGO | Web | Global | 24
38 | D10.3 | Formulate strategic media and communications plan | WP10 | NIKHEF | R | PU | 24
39 | D10.4 | Complete bank of graphics and multimedia resources | WP10 | IFAE | R | Global | 36
40 | D10.5 | Launch ECR mentorship and training programme | WP10 | UKRI | R | PU | 44