## Slide 1: ET-PP INFRA-DEV WP5 Progress Report Barcelona, June 12th 2023
R.Flaminio
A.Freise
R.Saban

## Slide 2: WP5 Outline
a short reminder of the objectives and the plan we had last year for
  The Project Office
  The Engineering Department
the progress since last year
  Where are we today with the PO and the ED
  The consultation within ET with other Work Packages
  The investigations for a possible collaboration with CERN on a number of topics
where do we go from here : a plan for the coming year(s)

## Slide 3: a short reminder …

## Slide 4: a short reminder …
WP5 is the Project Office and the Engineering Department

## Slide 5: The Project Office The pillars
  The Configuration PBS, Requirements, Design, Parameters, Layouts, TDR
  The Schedule WBS, Risk register, Financial Plan
  The Cost Estimate PBS, WBS, TDR, Risk register, Financial plan
The Project Office needs the following three Project Management pillars to be able to fulfil its mandate
Courtesy Alessandro Variola

## Slide 6: The first step: The Product Breakdown Structure – the WG
An ad hoc Working Group was appointed by the Executive Board and the Project Directorate.
Its mandate and the rules for the procedures are detailed in ET-0026A-23 in TDS.
Plenary meetings take place every month, each body builds up its own bit of the PBS.
Once the PBS is completed, the Technical Coordinator, will be in charge of the cross verification and the final editing.
Alessandro Variola, Head​ of the Project Office
Alessio Rocchi, Project Office Technical Coordinator​
Patrick Werneke, Head​ of the Engineering Department
Christian Olivetto, Project Office Configuration Manager​
Luca Latronico, Project Office Quality Manager​
Jan Harms, Co-chair​ of the Instrument Science Board
Stefan Hild, Co-chair​ of the Instrument Science Board
Patrice Verdier, Co-chair​ of the Electronics Infrastructure Board
Domenico D’Urso, Co-chair​ of the Site Preparation Board
Courtesy Alessandro Variola
The composition of the WG

## Slide 7: The Product Breakdown Structure – the outcome
Three PBS items have so far been defined by the Project Office and the Collaboration working closely together. These are :
Interferometers 908 units
Civil Infrastructures 707 units,
E-Infrastructures 71 units.
The WG had four plenary meetings and produced a close-out document, (ET-0170A-23) describing:​
  The goals​ of the PBS
  The strategy​ which was followed
  The rules for the procedures
  The PBS management plan​
  The PBS related roles​
  The traceability method​
  The proposed nomenclature
All the documentation related to the PBS is available in the ET Wiki:​
https://wiki.et-gw.eu/Main/PBSWorkingGroup/WebHome
Courtesy Alessandro Variola

## Slide 8: Building up the Configuration
Work has already started as an extension of the activity of the PBS WG. A document describing the mandate, the rules and the proposed activity has been prepared and verified. It will be referenced in TDS.
Given the priorities, the configuration process started with two parameter classes for each PBS unit:
  Functional parameters
  Integration parameters
The methodology will follow the one used for the PBS, which implies the need for a configuration database.
An agile ‘design phase’ change request process will be proposed.
Courtesy Alessandro Variola

## Slide 9: a short reminder …

## Slide 10: Selecting a computer assisted environment for documentation
The Project Office set the availability of a document lifecycle tool as the priority.
Courtesy Alessandro Variola
The features, the compatibility and the characteristics of four different systems were extensively analysed and compared to the requirements
  Atrium (CNRS)
  EDMS (CERN)
  ESS-DTL DMS, based on Alfresco@INFN
  TDS (Virgo and ET Collaboration)
and a report was sent to the Project Directorate.
PLM analysis and CAD survey are the next steps which will be integrated in the general configuration context.

## Slide 11: The deliverables of the Project Office

## Slide 12: The session on the Project Management Tools

## Slide 13: a short reminder …

## Slide 14: The fields of competence of the ED
Access Control
Cooling
Cryogenics
Electricity Distribution
Site Monitoring
Vacuum
Ventilation
Civil Engineering
  Surface
  Underground
  Shafts
Mechanical Engineering
Technical Coordination in the Field
Transport and Handling

## Slide 15: The session on the ED this afternoon
Organization of the Engineering Department | Patrick Werneke
Activities of the Civil Engineering | Maria Marsella
Interference of the Beampipe and Civil Infrastructures | A working session
Courtesy Patrick Werneke

## Slide 16: The consultations within ET with other Work Packages
The Executive Board and the ISB | for steering Project Office activities and the data collection
Liaison Group of WP7 | to provide input for the Innovation Plan
In preparation for the procurement activity of the Engineering Department, once the ideas on the style of the governance mature, other domains, like procurement processes, should be explored.

## Slide 17: The on-going investigations for a possible collaboration with CERN on a number of topics
Safety | A one day seminar was organised at CERN to assess whether or not the CERN HSE Unit could become an inspirational model for a similar unit for the Einstein Telescope. See report ET-0208A-23 in TDS.
Engineering Data Management System | Discussions are ongoing, but two meetings already took place, to explore the functionalities and the setting up of a possible collaboration.
Engineering Department | A meeting at CERN is organised for October 18th 2023 to explore possible fields of collaboration with the Engineering Department there.

## Slide 18: Personnel
Still vacant, recruitment
process was re-launched
Recruited in Paris
Recruited in Annecy
Still vacant
Still vacant, recruitment
process was re-launched
Still vacant, recruitment
process was re-launched
In office
In office
In office
In office
Recruited
After almost one year, three INFRA-DEV PP positions remain vacant despite repeated recruitment attempts !

## Slide 19: In-kind personnel
CNRS In-kind
  Parameter, Layout, Risk Christian Olivetto, Joseph Martino
  Software environment Remi Barbier, Patrice Verdier
NIKHEF In-kind
  Head of the Engineering
  Department Patrick Werneke
  Vacuum Engineer Marije Barel
  Systems Engineer remains to be recruited
INFN In-kind
  Technical Coordinator Alessio Rocchi 80%
  Civil Engineer Maria Marsella and her team 100%
  Head of the Project Office Alessandro Variola 80-100%
  Quality Manager Luca Latronico 25%
Joined during the course of this year

## Slide 21: … where do we go from here ?
Catch up with what we have failed to deliver. In particular, the recruitment of the resources funded by INFRA-DEV.
Continue to develop the activities of the Project Office and the Engineering Department closely working together with the Collaboration
As we progress with the definition of the modus operandi of the Project Office and of the Engineering Department, new needs for human and material resources come into focus.

## Slide 22: Acknowledgments
Alessandro Variola
Rémi Barbier
Luca Latronico
Maria Marsella
Joseph Martino
Christian Olivetto
Alessio Rocchi
Patrice Verdier
Patrick Werneke
Patrick Werneke
Marije Barel
Maria Marsella
Benoit Delille
Julia Double
Katy Foraz
Angela Goehring-Crinon
Sonja Kleiner
Joanne Madden
Rui Samoes
Jean-Philippe Tock
David Widegren
Domenico D’Urso
Gianluca Gemma
Jan Harms
Stefan Hild
Harald Lück
Michele Punturo
Project Office Activities
CERN
Engineering
Department
Activities
Paolo Chiggiato
Luigi Scibile
… and Mario Martinez-Pérez