## Slide 1: Towards the TDR
Document ID | ET.IDV.05.00.SMT.00007 | 
Author: A.Rocchi/A.Variola/L.Latronico | Verified: A.Rocchi/A.Variola/L.Latronico | Verified: A.Rocchi/A.Variola/L.Latronico
Document type | Meeting Slides | 
Status | Approved | 
Alessio Rocchi, INFN sezione Roma2
Alessandro Variola, INFN sezione Roma1
Luca Latronico, INFN sezione Torino
ET-PP INFRADEV Annual Meeting
Barcellona, 12-13/06/2023
ET-0YYYA-23

## Slide 2: A TDR should….
Provide the project scientific motivation.
Provide the results of the R&D proposed in the CDR and the validation process.
Summarize the main systems and elements requirements.
Technical and functional description of the systems and of the adopted solutions – Hardware, IT, Infrastructure, Safety. ( and layouts…).
Provide, for systems and elements, parameters and specifications. Elements engineering specifications shall be privileged in respect the systems functional description. (Tables)
Provide an installation and integration plan to support the studies and the costing.
Provide a description of the safety management.
Provide the basic elements for project management : schedule (master), cost estimate for procurement, installation, integration, operation (and dismantling if possible).
The master schedule shall be based on a WBS (Wp description) – High tiers.
Provide the description of the risk analysis elements and first version of the risk matrix, (at least the technical ones, TRL evaluation)

## Slide 3: We have three TDR…priorities
1) Civil infrastructures
2) Interferometers
3) E- infra

## Slide 4: So….
These are correlated, careful definition of the interfaces – Requirements policy
Definition of what process for verification and validation – Common procedure
Definition of the roles
Definition on how to ‘synchronize’ with other ‘local’ activity

## Slide 5: TDR Tentative lifecycle
Baseline Configuration
PBS units functional parameters
PBS Units integration parameters
PBS cross analysis for interfaces
Roles definition
Change process
Specifications
Engineering units specifications
As design Configuration
Safety constraints
Installation and integration plan
PM
WBS
Master schedule
Cost
Safety agreement
Risk register
Requirements
KPP
Requirements hierarchy and constraints definition
Traceability
Functional PBS units Requirements
Interfaces Requirements
Safety constraints
Installation and integration requirements
Roles definition
TDR
Roles definition
Editing
Verification
Validation
Configuration
Requirements
Project Definition
Specification
TDR

## Slide 6: Tentative Roadmap
TDR Process. The box length
is proportional to the duration.
TDR Deliverables. Each deliverable is
represented by a document

## Slide 7: Baseline
1) Define a baseline configuration:
CDR as reference
PBS as hierarchy backbone
functional parameters tables
integration parameters tables
functional layouts
change process
Goal : provide a baseline design and alternative solutions
Deliverables : baseline and alternative configuration (datas), CDR n.0 – approved (document)

## Slide 8: Requirements
1) Define the requirements
CDR, Coba document, parameters and layouts as reference
PBS as hierarchy backbone
functional requirements
interfaces requirements and management
installation and integration requirements
safety requirements
constraints
KPP
Goal : provide the correct input for the engineering phase. Provide all the inputs for the civil infrastructures' studies.
Deliverables : requirements database (datas), layouts (design), safety constraints (datas)

## Slide 9: Project Definition
1) Define the project management contribution
PBS, layouts, requirements and integration plan as reference
WBS
schedule
(at least technical) risk analysis
costing
safety agreement
Goal : provide the correct input for the cost and schedule assessment and management
Deliverables : WBS (data), schedule (Gantt), risk matrix (table), cost book (document).

## Slide 10: Engineering
1) Define the ‘as design’ configuration
Requirements, CDR, configuration and layouts as reference
PBS elements as backbone
PBS elements specifications
PBS units technical description
utilities matrix
R&D results
technical risk analysis
Goal : provide the correct input for the procurement/production phase
Deliverables : requirements database (datas), layouts (design), safety constraints (datas)

## Slide 11: TDR
1) Edit the TDR
All the previous as reference
PBS structure as technical backbone
Define the roles
TDR editing
TDR verification
TDR validation
TDR approval
Goal : provide the 3 TDR’s
Deliverables : civil infrastructure TDR, detector TDR, E infrastructure TDR

## Slide 12: E-infrastructures discussion
More uncertain scenario, at least for the solutions
Objectives should anyway be defined
Definition of a present baseline is possible? It should be at least be provided the interfaces with the civil infrastructures.
Undefined systems and solutions – do we need an Agile environment?

## Slide 13: Open discussion
Do we agree on the first slide? Can we produce a TDR topics template?
What about the tentative roadmap?
Have we all the resources and competences available?
What Verification and Approval process?
What organization ?
What approximation for costing and schedule ?
How to merge local initiatives?
What framework and processes for E-infrastructures ?

## Slide 14: Spares

## Slide 15: PBS and requirements
Mission (KPP)
Global (KPP)
Physics
PBS
Functional
Performance
Interface
Constraints
Crosscutting
Environment
Safety
Human factor
Risk (reliability)
Standards
Constraints (not technical)
Others
Is ConOps or
Project Roadmap
needed?

## Slide 16: PO and ED activities
- Safety analysis
- PBS with # elements
- WBS&Schedule
- Cost estimate
- Engineering specifications
- Civil infrastructure design
- Integration plan
- Risk analysis
- PMP summary