## Slide 1: Material for discussion on
Luigi SCIBILE for the ET-CERN collaboration
ET-PP INFRA-DEV Annual Meeting, Barcelona, 12-13 June 2023
Interfaces/Interferences between the beampipe and civil infrastructure
Initial plans for installation, length of beampipes, welding location, logistics, etc.

## Slide 2: Interfaces/Interferences between the beampipe and civil infrastructure: Overview
    The interreferences/interfaces between the beampipe and the civil infrastructure have to be identified throughout the beampipe lifecycle.
Transport
Transport
Heavy handling
Transport
Transport
Tunnel
installation and commissioning
Operation and Maintenance
Decommissioning
Manufacturing
Manufacturing
Materials

## Slide 3: Interfaces/Interferences between the beampipe and civil infrastructure: Overview
    Road network(s): depending on manufacturing strategy (on-site/off-site).
Transport
Transport
Heavy handling
Transport
Transport
Tunnel
installation and commissioning
Operation and Maintenance
Decommissioning
Manufacturing
Manufacturing
Materials

## Slide 4: Interfaces/Interferences between the beampipe and civil infrastructure: Overview
    Building(s): depending on manufacturing strategy (on-site/off-site)
Transport
Transport
Heavy handling
Transport
Transport
Tunnel
installation and commissioning
Operation and Maintenance
Decommissioning
Manufacturing
Manufacturing
Materials

## Slide 5: Interfaces/Interferences between the beampipe and civil infrastructure: Overview
    Shaft(s)*: specifications depends on beampipe length (using+ 15 meters )
Transport
Transport
Heavy handling
Transport
Transport
Tunnel
installation and commissioning
Operation and Maintenance
Decommissioning
Manufacturing
Manufacturing
Materials
(*) Assuming no inclined tunnel access
(+) Note that in ET design report update 2020 pipe lenght is 20 meters

## Slide 6: Interfaces/Interferences between the beampipe and civil infrastructure: Overview
    Caverns: Interfaces/Interferences depend on beampipe length and width for the transport during the installation and for the eventual replacement of a tube section in case of failure.
Transport
Transport
Heavy handling
Transport
Transport
Tunnel
installation and commissioning
Operation and Maintenance
Decommissioning
Manufacturing
Manufacturing
Materials

## Slide 7: Interfaces/Interferences between the beampipe and civil infrastructure: Overview
    Tunnel: Interfaces/Interferences depend on many factors (see separate slides).
Transport
Transport
Heavy handling
Transport
Transport
Tunnel
installation and commissioning
Operation and Maintenance
Decommissioning
Manufacturing
Manufacturing
Materials

## Slide 8: Interfaces/Interferences between the beampipe and the tunnel: cross section
    Space required for the supporting structure, for welding and future inspections (min 400mm), for gate valves, for pumping modules and related control units (depending on design installation).
800
1100
1100
800
500
2460
1100
800
400
2720

## Slide 9: Interfaces/Interferences between the beampipe and the tunnel: cross section
    Space required for welding and future inspections (min 400mm)
800
1100
1100
800
500
2460
1100
800
400
2720

## Slide 10: Interfaces/Interferences between the beampipe and the tunnel: cross section
1100
800
400
2720
    Space required for supporting structure (assuming that the support infrastructure will be installed along with the tubes).
2180
1100
800
400
2720
2180

## Slide 11: Interfaces/Interferences between the beampipe and the tunnel: cross section
    Space required for pumping modules (up to 550mm)
800
1100
1100
800
500
2460
1100
400
2720

## Slide 12: Interfaces/Interferences between the beampipe and the tunnel: cross section
Space required for sectional gate valves (DN1000)
800
1100
1565 (W+V) x 2751 (L +M) x 356 (P) mm
+ 140 mm (Q)

## Slide 13: Interfaces/Interferences between the beampipe and the tunnel: Transport/Weldings/Logistics
    During the installation of the tubes, transport will take place in the tunnel within the allocated space during the nights (Reduce co-activity, enhance safety and prepare the work for the day shift)
    Assuming two circular welds per working day per team, 10 circular welds per week per team
    The current welding strategy is to be carried out at the final location. A clean tent will be moved to the welding location to allow the removal of the tubes clean seals before the welding.
1100
800
400
2720

## Slide 14: Interfaces/Interferences between the beampipe and the tunnel: Questions?
    Fire fighting equipment (water - DN200 pipe?)
    Cable trays for communication equipment?
    Ventilation and smoke extraction?
    Presence of alcoves/enlargements?

## Slide 15: Interfaces/Interferences between the beampipe and the tunnel: Questions?
    Space required to dismount a part of the beampipe in case of serious issues once the towers are mounted?

## Slide 16: Installation and logistics scenarii

## Slide 17
Warehouse storage
Site buffer storage
Transport
Heavy handling
Transport
Material Bakeout @450°
Installation and logistics: off-site manufacturing
Cleaning
Leak testing
X [m] section pipe preparation
x 12 10-6 [m] / X (= 8000 for X = 15)
Welding, assembly and transport of 312.5 m sections
5km (10km)
Bakeout @150°
Leak testing
x 16 (x32)
x 12
Option 1 (Option 2)
Vacuum systems installation and testing
x 2 (x1)
Beam pipe ready for operation
Vacuum pumping
x 12
TUNNEL
Potential Parallel operation
Potential parallel activtiy
Design dependence
Transport
Option 1: 10km sector
Option 2: 5km sector

## Slide 18
Site buffer storage
Heavy handling
Material Bakeout @450°
Installation and logistics: on-site manufacturing
Cleaning
Leak testing
X [m] section pipe preparation
x 12 10-6 [m] / X (= 8000 for X = 15)
Welding, assembly and transport of 312.5 m sections
5km (10km)
Bakeout @150°
Leak testing
x 16 (x32)
x 12
Option 1 (Option 2)
Vacuum systems installation and testing
x 2 (x1)
Beam pipe ready for operation
Vacuum pumping
x 12
TUNNEL
Potential Parallel operation
Potential parallel activtiy
Design dependence
Transport
Option 1: 10km sector
Option 2: 5km sector

## Slide 19
Heavy handling
Welding, assembly and transport of 312.5 m sections
5km (10km)
Bakeout @150°
Leak testing
x 16 (x32)
x 12
Option 1 (Option 2)
Vacuum systems installation and testing
x 2 (x1)
Beam pipe ready for operation
Vacuum pumping
x 12
Installation and logistics: in-tunnel manufacturing
TUNNEL
Cleaning
Leak testing
X [m] section pipe preparation
x 12 10-6 [m] / X (= 8000 for X = 15)
Material Bakeout @450°
Transport
Potential Parallel operation
Potential parallel activtiy
Design dependence
Manufacturing can only start after the completion (or partial completion) of the underground infrastructure.
Option 1: 10km sector
Option 2: 5km sector

## Slide 20
Heavy handling
Welding, assembly and transport of 312.5 m sections
5km (10km)
Bakeout @150°
Leak testing
x 16 (x32)
x 12
Option 1 (Option 2)
Vacuum systems installation and testing
x 2 (x1)
Beam pipe ready for operation
Vacuum pumping
x 12
Installation and logistics: in-tunnel quasi-continuous
TUNNEL
Cleaning
Leak testing
X [m] section pipe preparation
x 12 10-6 [m] / X (= 384 for X = 312.5)
Material Bakeout @450°
Transport
Potential Parallel operation
Potential parallel activtiy
Design dependence
Quasi-continuous
Manufacturing can only start after the completion (or partial completion) of the underground infrastructure.
Option 1: 10km sector
Option 2: 5km sector

## Slide 21: Installation sequence, logistics and timelines/schedules - Options
    One option (on-site manufacturing) analysed for the installation sequence with a feasible logistics using a time-location diagram.
    It only represents a preliminary overview. It will be updated once a more complete Work Breakdown Structure (WBS), activity list and production rates will be available
    It provides a method (1) to study the technical and safety feasibility of potential parallelisms and (2) to highlight scheduling constraints for the eventual options.
Time-location example:
ET four tubes in one arm

## Slide 22: Timelines/schedules – example

## Slide 23: Timelines/schedules – example
32 sectors x ARM
Up to 8 Parallel Teams
45 months from start installation to @ vacuum.