## Slide 1: WP4 Parallel Session Summary

## Slide 2
 | Deliverable | Current Status | Mitigation | Estimate
M 4.1 | Document detailing site-specific characteristics that impact ET sensitivity and its duty cycle Lead institute: Nikhef, timing: 9/22 + 10 = 7/23 | Report published, was considered not quantitative enough | Will be updated (by inserting referenced documents) and resubmitted. | End 6/24
M 4.2 | Common methodology to estimate impact of site characteristics on ET sensitivity and operation, and if required, a scheme to compensate it Lead institute: INFN, timing 9/22 + 15 = 12/24 | Milestone not yet met. Common methodology is still being developed. Delayed by different site time lines. | Discussion in SPB/WP4, and host sites. Developing a more realistic timeline for individual methodologies to be published 9/24. | 6/24 first draft
D 4.1 | Scan of legal procedures, permitting and land acquisitions (steps to be taken prior to starting excavations) Lead institute: Nikhef, timing: 9/22 + 10 = 7/23 | Delivered |  | Delivered
D 4.2 | Updated socio-economic impact studies. Scan of accessibility, quality of life etc. Lead institute: INFN, timing 9/22 + 15 = 12/23 | Update is being worked by individual local teams, but will still be limited due to incomplete information (localization, subsurface geology, geo-technical understanding). | Maintain an updated view based on new incoming information. | 10/24 for updated view
D 4.3 | Complete quantification of all aspects impacting ET performance for both sites Lead institute: UW, timing 9/22 + 28 = 1/25 | Depending somewhat on current work progress, and teams availability, discussions with ETO | Work according to plan and contracts, discussions in SPB, ET Symposium | Expected 12/24 9/24 new time line
D 4.4 | 3D Geology, hydro-geology and modeling Lead institute: INFN, timing 9/22 + 30 = 3/25 | Work ongoing, main body of activities at both sites. Local site funding and contracting result in different timeline | Work according to plan and contracts. Redefining and optimized workflow and resonsibilities between Sites and ETO | Sardinia: being discussed in contract EMR: expected 1/26
D 4.5 | Updated cost and schedule estimates of excavations, including noise cancelation, surface preparation costs (permiting, debris removal, land acquisition etc.) Lead institute: Nikhef, timing 9/22 + 42 = 3/26 | Work ongoing, main body of activities at both sites. Local site fundunding and contracting result in different timeline | Work according to plan and contracts. Redefining and optimized workflow and resonsibilities between Sites and ETO | Sardinia: 6/25 EMR: 6/26
WP4 – Update June 16th 2024

## Slide 3
Definition of
Relevant Measurements
Definition of
Science Cases
Definition of
Analysis Recipes
Site Noise Measurement: data acquisition and validation
Definition of
Tools for detector behavior
SUPPORT
Result Validation by ETC
Evaluation of Det. Performance using common tools and recipes
Result Validation by ETC
NO
YES
Analysis for noise mitigation strategies
NO
Risk assessment of mitigation effectiveness
YES
Evaluation of Det. Perf. Including mitigation
Site Comparison:
Common Methodology

## Slide 4: Possible New SCB Structure
Working Divisions | Topics | Output | WP
Noise measurements | Update of the needed physical variables for the site characterization Update of surface and underground (and/or borehole) accurate noise measurements, with procedures and standards Coordination of the measurement campaigns at the candidate sites (ongoing and planned) Interaction with the host teams to have comparable long/short-term, active/passive measurements Set of standard data formats, repository and analysis tools. Site data management | Document describing a set of physical variables to be acquired by the Host Teams. Documents describing standard for measurements Documents describing common data formats and analysis tools | Seismic Noise Gravimetry and Geodynamics Magnetic noise Other Env. Noise
Noise Impact Evaluation | Common methodologies to evaluate the impact of environmental noise on detector performance Common methodologies to elaborate possible site noise mitigation strategies Validation procedure of local team results Site preservation strategy coming from noise impact. Risk assessment. Coordination of local team studies | Document describing a common methodology to evaluate site dependent detector performances Document describing a possible site noise mitigation strategy Document describing a validation procedure of local team results Document describing a methodology to evaluate the probability and the severity of risk related to site dependent detector performance | OSB Interface ISB Interface
3D Geological and geotechnical evaluation, and modeling. | Definition of minimal set of (hydro-)geological, geophysical, and geotechnical investigations to be performed by the Host Teams Coordination of local team effort and promote data/methods exchanges Provide subsurface images at defined regional locations, such as tunnels and caverns. Derive structural model and rock quality model Define groundwater conditions in terms of pressure and flow | Document describing a minimal set of geo parameters to create 3D models and maps on. Documents describing the standards for a local site document providing the geotechnical perspective that the proposed detector can be build. 3D maps of predefined subsurface parameters for the volume enclosed by ET, extended to a region considered relevant | Structural Geology Hydrogeology Geotechnology Geophysics Interfaces with ETO