## Slide 1: WP4 Parallel Session

## Slide 2
 | Deliverable | Current Status | Mitigation | Estimate
M 4.1 | Document detailing site-specific characteristics that impact ET sensitivity and its duty cycle Lead institute: Nikhef, timing: 9/22 + 10 = 7/23 | Report published, was considered not quantitative enough | Will be updated (by inserting referenced documents) and resubmitted. | End 6/24
M 4.2 | Common methodology to estimate impact of site characteristics on ET sensitivity and operation, and if required, a scheme to compensate it Lead institute: INFN, timing 9/22 + 15 = 12/24 | Milestone not yet met. Common methodology is still being developed. Delayed by different site time lines. | Discussion in SPB/WP4, and host sites. Developing a more realistic timeline for individual methodologies to be published 9/24. | 6/24 first draft
D 4.1 | Scan of legal procedures, permitting and land acquisitions (steps to be taken prior to starting excavations) Lead institute: Nikhef, timing: 9/22 + 10 = 7/23 | Delivered |  | Delivered
D 4.2 | Updated socio-economic impact studies. Scan of accessibility, quality of life etc. Lead institute: INFN, timing 9/22 + 15 = 12/23 | Update is being worked by individual local teams, but will still be limited due to incomplete information (localization, subsurface geology, geo-technical understanding). | Maintain an updated view based on new incoming information. | 10/24 for updated view
D 4.3 | Complete quantification of all aspects impacting ET performance for both sites Lead institute: UW, timing 9/22 + 28 = 1/25 | Depending somewhat on current work progress, and teams availability, discussions with ETO | Work according to plan and contracts, discussions in SPB, ET Symposium | Expected 12/24 9/24 new time line
D 4.4 | 3D Geology, hydro-geology and modeling Lead institute: INFN, timing 9/22 + 30 = 3/25 | Work ongoing, main body of activities at both sites. Local site funding and contracting result in different timeline | Work according to plan and contracts. Redefining and optimized workflow and resonsibilities between Sites and ETO | Sardinia: being discussed in contract EMR: expected 1/26
D 4.5 | Updated cost and schedule estimates of excavations, including noise cancelation, surface preparation costs (permiting, debris removal, land acquisition etc.) Lead institute: Nikhef, timing 9/22 + 42 = 3/26 | Work ongoing, main body of activities at both sites. Local site fundunding and contracting result in different timeline | Work according to plan and contracts. Redefining and optimized workflow and resonsibilities between Sites and ETO | Sardinia: 6/25 EMR: 6/26
WP4 – Update June 16th 2024

## Slide 3
M 4.1: Document detailing site-specific characteristics that impact ET sensitivity and its duty cycle
DRAFT End of June24
M4.2: Common methodology to estimate impact of site characteristics on ET sensitivity and operation, and if required, a scheme to compensate it DRAFT available
D4.2: Updated socio-economic impact studies. Scan of accessibility, quality of life etc.
DRAFT Oct. ?
D4.3: Complete quantification of all aspects impacting ET performance for both sites
Expected Dec/24 to be moved to ???

## Slide 4: Site Comparison: Common Methodology

## Slide 5: ET-PP Milestone M4.2: Methodology
Define relevant measurements to be performed, following specific standards
Define science cases relevant for site dependent detector performance, likely low frequency scientific targets
Define tools to be used to estimated detector behavior, given a specific environmental configuration
Define analysis recipes to be followed to evaluate detector potentialities with respect to science cases of point 2
Evaluation of detector performance
Result validation
Define a possible mitigation strategy for environmental noise and evaluate possible additional costs
Evaluation of detector performance considering mitigation strategies of point 6
Result validation
Risk assessment of scientific descoping taking into account results obtained in point 5 and point 8

## Slide 6
Definition of
Relevant Measurements
Definition of
Science Cases
Definition of
Analysis Recipes
Site Noise Measurement: data acquisition and validation
Definition of
Tools for detector behavior
SUPPORT
Result Validation by ETC
Evaluation of Det. Performance using common tools and recipes
Result Validation by ETC
NO
YES
Analysis for noise mitigation strategies
NO
Risk assessment of mitigation effectiveness
YES
Evaluation of Det. Perf. Including mitigation

## Slide 7: Definition of Science Cases and of Analysis Recipes
There is a huge effort in the ETC to define the science case for the Einstein Telescope. This involves studies of different detector configurations, construction of the data analysis platform, exploration of the computational needs for optimum science extraction and the interaction between ET and other GW/non-GW observatories.
The Observational Science Board (OSB) of ETC is fully devoted to identify ET science goals and provide common tools and an analysis platform. OSB will provide the list of science cases that needs or may benefit of low frequency GW detection, the recipes and common tools to be used by local teams in their analysis.

## Slide 8: Definition of Tools for detector behavior and Mitigation Strategy
In the ETC the Instrumental Science Board (ISB) has been established to develop the ET Detector Technical Design Report. ISB is structured in different Working Divisions and it will provide the tools to estimate the effect of different site environmental noises on detector behavior and possible mitigation strategy to compensate them.
  magnetic noise: VIRGO tools
  NN noise: A beginner guide to the installing and running basic pygwinc noise budget (by Mikhail Korobko) https://wiki.et-gw.eu/ISB/Interferometer/ObservatoryDesignAndNoiseBudget/BeginnerSGuideToInstallingAndRunningPygwinc

## Slide 9: Definition of Relevant Measurements
The environment has an important role in a third-generation gravitational wave (GW) observatory like ET, which one of the most crucial goals is to observe GW in the frequency range 2-10 Hz.
ETC established a board fully devoted to define the relevant site parameters for detector functionality, the Site Characterization Board, that is providing the list of relevant measurements to be performed in each candidate site and the standard to be followed.
SPB documents:
M1.1: physical variables: ET-0012A-23, discussed and finalized at the II SPB Workshop (Jan 2023) https://apps.et-gw.eu/tds/?content=3&r=18113
M1.2: measurements recommendations and standards: ET-0013A-23, discussed and finalized at the II SPB Workshop (Jan 2023) https://apps.et-gw.eu/tds/?content=3&r=18114
M1.3: data format standards and analysis tools ET-0270A-23, https://apps.et-gw.eu/tds/?content=3&r=18398

## Slide 10: Site Noise Measurement: data acquisition and validation
Measurements should follow standards set by ETC. Local team have to provide all the quantities identified by ETC with verified and well documented tools to perform a basic analysis. Data and tools should be well documented and shared to the whole ETC:
  Long term measurement (at least two years, 3 broadband component)
  Short-term measurement
  gravimetry & geodynamics studies
  magnetic noise

## Slide 11: Evaluation of Detector Sensitivity and Validation
Following the inputs and making use of common tools and recipes provided by the different bodies of ETC, local teams must evaluate the detector sensitivity for each of the identified science targets.
Results of local team studies should be verified by the relevant ETC bodies to ensure that common tools and recipes have been correctly used.

## Slide 12: Evaluation of Det. Perf. Including mitigation
ISB should provide possible mitigation strategies to compensate env. Noise. Local team may evaluate detector performance taking into account mitigation strategies in agreement with what has been defined by ETC that has to validate the results of the study

## Slide 13: Risk assessment of mitigation effectiveness
Based on the obtained results, local team should assess the risk of a possible scientific descoping due to effectiveness of mitigation strategies, estimating additional costs and time and personpower.

## Slide 14: Timeline
In the ESFRI Proposal there was a clear timeline for the output of the process: M28 (end of 2024!)
Define relevant measurements
  Data Availability Sardinia 6.2024, EMR 2.2026
Define Science Cases by ETC (Oct. 24 ?)
Common tools to simulate detector behavior already available:
https://gitlab.et-gw.eu/et/isb/interferometer/ET-NoiseBudget/-/tree/master/acoustic_spectra?ref_type=heads
Start of impact quantification by local team ???