## Slide 1: ET-PP WP9 2nd review meeting (RP2)
15/05/2025
Grant agreement: Nº 101079696
Project: 101079696 — ET-PP — HORIZON-INFRA-2021-DEV-02
Horizon Europe:
Coordination and Support Actions

## Slide 2: WP9- Sustainable Development Strategy: Introduction and objectives
Project: 101079696 — ET-PP, 2nd review meeting
Preparatory Phase for the Einstein Telescope Gravitational Wave Observatory
2nd review meeting (RP2) — 15.05.2024
Develop a strategy for the realization of a sustainable RI, including:
Study and minimize the carbon footprint of ET, including computing and travel
Evaluate and minimize the landscape and environmental impact
Evaluate the contribution of the infrastructure to the UN sustainable goals
EGO
INFN
MUL
Lead beneficiary and Co-Coordinator - Responsible for:
M17, M18, M19, D9.3 (ET CO2 footprint)
Co-coordinator
Responsible for:
D9.1 (ET SD strategy), D9.2 (ET env. Impact)
Participant (expertise: excavated material treatments)- Contributor to D9.2
WP9 participants
Francesca Spagnuolo (EGO)
Maria Marsella (INFN)
Co-Coordinators
Objectives
WP9 Team
CNRS has withdrawn its direct involvement in WP9 after reaching M18 and will now serve as reviewer for WP9 milestones & deliverables
DESY will join after 2RP review meeting
Robert Galler (MUL)
Monica Marzario (INFN)
Gabriel Loucky (MUL)
Disha Sawant (EGO)

## Slide 3: WP9: Tasks
Project: 101079696 — ET-PP, 2nd review meeting
Task 9.1 ET carbon footprint assessment and mitigation
Subtasks:
    9.1.1 ET carbon budget
    9.1.2 ET energy consumption optimization
2nd review meeting (RP2) — 15.05.2024
Preparatory Phase for the Einstein Telescope Gravitational Wave Observatory
M1-M48
Task 9.2 Landscape, environmental and societal impact
Subtasks:
9.2.1 Assessing and minimizing the ET impact on its environment
9.2.2 Environmental management approach
9.2.3 Analyse and define an overall strategy for reclamation, reuse and recycling of the excavated materials

## Slide 4: WP9: Task 1
Project: 101079696 — ET-PP, 2nd review meeting
ET carbon fooprint assessment and mitigation
Subtasks:
    9.1.1 ET carbon budget
    9.1.2 ET energy consumption optimization
2nd review meeting (RP2) — 15.05.2024
Preparatory Phase for the Einstein Telescope Gravitational Wave Observatory
RP2: M13-M30
Identified the categories that will contribute more to the ET footprint (e.g. energy use; transport/travel; computing, etc.) in the different phases (e. g., construction, operation, etc.)
Elaborated a plan to develop an accurate ET CO2 footprint assessment & related mitigation strategy (D9.3 > to be delivered by October 31st, 2025)

## Slide 5: ET CO2 footprint assessment and mitigation strategy
Project: 101079696 — ET-PP, 2nd review meeting
2nd review meeting (RP2) — 15.05.2024
Preparatory Phase for the Einstein Telescope Gravitational Wave Observatory
  Baseline Emissions Analysis: Use LCA principles to calculate current CO2 emissions associated with materials, energy, and transportation.
  Develop Emissions Scenarios: Model emissions under various scenarios, including:
    Business-as-usual (BAU): No significant interventions.
    Moderate Mitigation: Partial adoption of sustainable practices.
    Aggressive Mitigation: Full integration of best practices, including renewable energy and circular economy principles.
  Evaluate Scenarios: Assess scenarios for feasibility, cost, and environmental impact.
  Deliverables (included in D9.3):
    CO2 Baseline Report.
    Scenario Analysis Report
CO2 Emissions Scenario Analysis

## Slide 6
Definition of CO2 Emissions Scenarios
Establish baseline emissions% and project future trends under different operational strategies
Develop detailed emissions scenarios to evaluate potential environmental impacts during the lifecycle of (LCA#) the ET
References: % Estimate of the carbon footprint of astronomical research infrastructures
# LCA by Uni Lieden
Project: 101079696 — ET-PP, 2nd review meeting
2nd review meeting (RP2) — 15.05.2024
Preparatory Phase for the Einstein Telescope Gravitational Wave Observatory
Construction Phase:
  Energy Consumption: The construction of the ET, particularly its extensive underground facilities, will require significant energy, leading to substantial greenhouse gas (GHG) emissions.
  Material Usage: The production and transportation of construction materials, such as concrete and steel, contribute to the project's carbon footprint.
  Site Disturbance: Excavation and land alteration can release stored carbon from soil and vegetation.
Operational Phase:
  Energy Demand: Operating the ET's advanced detection systems and maintaining optimal conditions (e.g., temperature control, vibration isolation) will consume considerable energy.
  Maintenance Activities: Regular maintenance may involve additional energy use and material consumption.
Decommissioning Phase:
Dismantling Infrastructure: The end-of-life phase involves energy use for dismantling structures and managing waste materials.
Baseline Emission Assessment

## Slide 7: WP9: Tasks
Project: 101079696 — ET-PP, 2nd review meeting
Task 9.2 Landscape, environmental and societal impact
Subtasks:
9.2.1 Assessing and minimizing the ET impact on its environment
9.2.2 Environmental management approach
9.2.3 Analyse and define an overall strategy for reclamation, reuse and recycling of the excavated materials
2nd review meeting (RP2) — 15.05.2024
Preparatory Phase for the Einstein Telescope Gravitational Wave Observatory
RP2: M13-M30
Offered an overview of the main expected impacts of ET in terms of landscape/environment and social sustainability
Envisaged the adoption of policies and rules to limit ET possible negative impacts on the environment (e.g. green responsible procurement practices)
Explained our strategy for the re-use of the excavated material and waste, in line with EU Law and strategies (e.g. the EU Soil Strategy 2030 > reuse excavation material in the same or another appropriate location whenever is possible)

## Slide 8: WP9: Tasks
Project: 101079696 — ET-PP, 2nd review meeting
Task 9.1 ET carbon footprint assessment and mitigation
Subtasks:
    9.1.1 ET carbon budget
    9.1.2 ET energy consumption optimization
2nd review meeting (RP2) — 15.05.2024
Preparatory Phase for the Einstein Telescope Gravitational Wave Observatory
M1-M48
Task 9.2 Landscape, environmental and societal impact
Subtasks:
9.2.1 Assessing and minimizing the ET impact on its environment
9.2.2 Environmental management approach
9.2.3 Analyse and define an overall strategy for reclamation, reuse and recycling of the excavated materials
Fixed some preliminary sustainability goals (15 PSGs), targets, timing and responsibilities > M17 Preliminary Sustainability Plan

## Slide 9
ET preliminary sustainability plan’s objectives and targets
Objectives | Sustainability Target | Responsibility | Timing
Implement sustainable practices in excavation | Reduce contamination and enhance material reuse | Engineering Department | By the end of the design phase
Enhance sustainable Construction techniques | Prioritize sustainable site design and sustainable practices (e.g. reduce energy usage; minimize waste, etc.) | Project Office and Engineering Department | Preparatory phase (end of 2026)
Obtain ISO 50001 Certification | Reduce energy consumption at the ET site. Increase the share of renewable energy in the energy mix. Improve energy efficiency. | Engineering Department > Technical Systems Service > Energy Manager | 1 year after ET reaches full operativity (operation phase)
Project: 101079696 — ET-PP, 2nd review meeting
2nd review meeting (RP2) — 15.05.2024
Preparatory Phase for the Einstein Telescope Gravitational Wave Observatory

## Slide 10
ET preliminary sustainability plan’s objectives and targets
Objectives | Sustainability Target | Responsibility | Timing
Adopt effective environmental management systems (in line with guidelines provided by the ISO 14000 series or similar) | Achieve efficient use of natural resources at the ET site. Reduce waste Soundly manage chemicals and all wastes in accordance with existing guidelines | ET Management Engineering Department | When ET starts operating and until the dismantling phase (operation and termination phases) Since the construction phase and until the dismantling phase (implementation, operation and termination phases)
Adopt sustainable practices for data management | Develop stable and robust repositories while ensuring that data are stored in an environmentally friendly manner Adopt digital technologies that offer green solutions (e.g. green cloud) | Engineering Department Information Technology Department > Computing Facilities and Data Storage Division | Since Preparatory phase 2 When ET starts operating and until the dismantling phase
Project: 101079696 — ET-PP, 2nd review meeting
2nd review meeting (RP2) — 15.05.2024
Preparatory Phase for the Einstein Telescope Gravitational Wave Observatory

## Slide 11
ET preliminary sustainability plan’s objectives and targets
Objectives | Sustainability Target | Responsibility | Timing
Adopt a Gender Equality Plan | Ensure a gender-equal working environment | Direction > Gender Equality Plan Manager | 6 months after ET reaches full operativity
Conduct annual audits to assess and monitor the implementation of the gender equality plan | Ensure a gender-equal working environment | Direction > Gender Equality Plan Manager | Annually
Adopt smart working agreements | Ensure a better work-life balance and improve the well-being of the employees | Administration > Human Resources Office | When ET starts operating
Promote safe and secure working environment in accordance with relevant national and international Standards (including ISO 45001) | Ensure productive employment and decent work for all, including people with disabilities | Health, Safety and Security Office/Department > Safety Manager | When ET starts operating and for all phases of the RI lifecycle
Project: 101079696 — ET-PP, 2nd review meeting
2nd review meeting (RP2) — 15.05.2024
Preparatory Phase for the Einstein Telescope Gravitational Wave Observatory

## Slide 12
ET preliminary sustainability plan’s objectives and targets
Objectives | Sustainability Target | Responsibility | Timing
Implement company carpooling and shuttle service from the nearest public transport facility to/from the ET site | Reduce emissions and promote sustainable mobility | Administration Department | When ET starts operating, and for all phases of the RI lifecycle
Adopt internal rules to ban or limit short-haul flights on routes where fast trains are available | Reduce emissions and promote sustainable mobility | Administration Department | Since the construction phase and until the dismantling phase (implementation, operation and termination phases)
Adopt sustainable procurement practices (in accordance with the ISO 20400 standard) and deliver periodic training courses on sustainable procurement to employees who interact directly with suppliers | Reduce waste and carbon emissions and manage efficiently available resources Enable compliance with social legislations (e.g. by buying ethical products and services whenever it is possible) | Administration > Procurement Office | When ET starts operating and during its lifecycle
Project: 101079696 — ET-PP, 2nd review meeting
2nd review meeting (RP2) — 15.05.2024
Preparatory Phase for the Einstein Telescope Gravitational Wave Observatory

## Slide 13
ET preliminary sustainability plan’s objectives and targets
Objectives | Sustainability Target | Responsibility | Timing
Enter into agreements with research centers and universities from all countries of the ET collaboration | Support educational programs for the development of specialized skills Co-design master courses and training programs | Direction | When ET starts operating and during its lifecycle
Engage the ET community | Develop capacity building and monitoring tools | Project Office and Engineering Department | Preparatory phase (end of 2026)
Commit to outreach activities | Promote citizen science and the understanding of science and technology in society at large | Communication office | Since the preparation phase and for all the lifecycle of the RI
Project: 101079696 — ET-PP, 2nd review meeting
2nd review meeting (RP2) — 15.05.2024
Preparatory Phase for the Einstein Telescope Gravitational Wave Observatory

## Slide 14: WP 9: Deliverables and milestones
Project: 101079696 — ET-PP, 2nd review meeting
2nd review meeting (RP2) — 15.05.2024
Delivered (anticipated)
M18 ET Sustainability Workshop (EGO, workshop+report, M18)
Completed
M17 Preliminary sustainability plan (EGO, report, due M11> submitted> sent back for revisions > ready for re-submission after passing internal and exernal review)
Delayed to October, 2025
D9.1- ET Sustainable Development Implementation Strategy (INFN, document/report, M18)
D9.2- ET Environmental Impact assessment and mitigation strategy (INFN, document/report, M24)
D9.3-ET CO2 footprint assessment and mitigation strategy (EGO, document/report, M36)
To be delivered in the next RP
M19 Final Sustainability Plan (EGO, reports, M47)
Preparatory Phase for the Einstein Telescope Gravitational Wave Observatory

## Slide 15: WP 9: Critical risks, deviations from Annex I, contingency plans
Project: 101079696 — ET-PP, 2nd review meeting
2nd review meeting (RP2) — 15.05.2024
Critical risks encountered in RP2
Difficulties to find full time personnel adequately in time, with the skills needed for the project
Delays in technical designs
To cope with these risks
increased time dedicated to cover the needs of the ET-PP project with in-kind contributions (person/months) and support from a consultancy service
adoption of reference scenario such as preliminary documents (ESFRI proposal) and baseline detector layouts designed by ETO (in progress)
Deviations from Annex I > partners efforts > withdrawal of a partner (CNRS)
Contingency plans > additional in-kind resources from other ET-PP partners
Preparatory Phase for the Einstein Telescope Gravitational Wave Observatory

## Slide 16: WP 9: Contribution from each partner
INSTITUTION |  | PM as per Annex I | PM in the period
CNRS | CONTRIBUTIVES | 13,00 | 4,73
 | REQUESTED EC | 0 | 0
EGO | CONTRIBUTIVES | 12,60 | 2,68
 | REQUESTED EC | 18,00 | 0
INFN | CONTRIBUTIVES | 39,20 | 3
 | REQUESTED EC | 18,00 | 0
MUL | CONTRIBUTIVES | 4,00 | 3,12
 | REQUESTED EC | 12,00 | 4,68
Total Person Months | CONTRIBUTIVES | 68,80 | 9,36
Total Person Months | REQUESTED EC | 48 | 5,85
 |  | 116,80 | 33,42
Project: 101079696 — ET-PP, 2nd review meeting
2nd review meeting (RP2) — 15.05.2024
Total PMs worked during RP1: 2,83 PMs

## Slide 17: WP 9: Outlook and perspectives
Project: 101079696 — ET-PP, 2nd review meeting
2nd review meeting (RP2) — 15.05.2024
Preparatory Phase for the Einstein Telescope Gravitational Wave Observatory
RP1
RP2
RP3
1 Sept 2022-31 Aug 2023
1 Sept 2023-28 Feb 2025
1 March 2025-31 Aug 2026
Reinforce WP9 team by the end of May 2025 (additional resources recruited during RP2 + DESY staff to join after May,15)
Deliver D9.1, D9.2 and D9.3 – by October 31st, 2025 > provide input and quantitative data for M19-Final Sustainability Plan
Workshop (coll.WP7) - Nov 13-14 2025 - Environmental Sustainability for large underground research infrastructures: challenges and innovative solutions for the ET project.
sustainability workshop (Paris Nov 17, 2023
revised version of the Preliminary Sustainability Plan prepared and submitted for internal/external review
recruitment of additional resources completed > sustainability expert (full time EGO); ARUP consultant (INFN)
first version of the Preliminary Sustainability Plan (M17)
design and organization of the sustainability workshop (M18)