## Slide 1
ET-PP Annual Meeting Barcelona 2025
WP6 (D6.3/D6.5) Deliverables discussions
Christian Olivetto
Notes: Today, we’d like to walk you through the methodology we propose to deploy and test, and collect your feedback so we can validate it for the next steps of the ET project.

## Slide 2
2
Preparation of WP6 deliverables: parrallel session 23/07
Following the meeting on 10/07/2025 between WP6 and WP5 coordinators, discussions focused on the following points:
- First discussion point:
Clarify the scope, objectives, and expected outcomes of deliverable D6.5 (Preliminary RI TDR). This clarification will allow us to validate the parameters of the deliverable more precisely and serve as a foundation for presenting the document at the conclusion of the ET-PP project.
- Second discussion point:
Move responsability of the deliverable D6.5 from WP6 to WP5
- Third discussion point:
Analyse of impact on Engineering Department and Project Office for ET-PP period but also for next phase of ET project
- Fourth point:
To prepare for any eventuality, discuss the consequences if we are unable to produce this deliverable on time.
Notes: The agenda of this presention will cover the following points,

## Slide 3
3
WP6 deliverables highlights (1)
Following the discussions, the main decisions or actions relate to the following points:
It has been proposed to move responsability of WP6 (D6.3) from WP6 to WP5
This D6.3 is in fact the pre-TDR deliverable with a delivery due date at the end of ET-PP.
The D6.5 (Final TDR) can be finalised only after site choice foreseen in 2028.
A specific meeting will be organized at the beginning of September 2025 with WP6, WP5 coordinators, local team managers with the aim to produce a skeleton document with the main objectives described below:
Notes: The agenda of this presention will cover the following points,

## Slide 4
4
WP6 deliverables highlights (2)
This D6.3 deliverable can’t be a standard TDR document but we have to redefine in CDR (Concpetual Design Report).
Define clearly the scope of document in this new proposal to EU officer
Define a proposal of table of contents of this document, with realistic objectives for obtaining information from the various working groups (local team)
Describe precisely the information and the process for obtaining it in order to finalise the TDR at a later date
Evaluate the feasibility of providing the information that this document must contain within the allotted time, question to ETO management.
Allocate responsibilities for writing and obtaining information in order to meet the deadline for the skeleton of this document, i.e. 15 September 2025.
Notes: The agenda of this presention will cover the following points,