## Slide 1: ET-PP (WP6.2) ET beampipe activities at CERN
Anité Pérez on behalf of the ET vacuum team at Barcelona, 05/05/2026
Project: 101079696 — ET-PP — HORIZON-INFRA-2021-DEV-02
ET vacuum team at CERN:
Carlo Scarcia; Carlotta Accettura; Cedric Garion; Gilles Favre; Giuseppe Bregliozzi; Gregory Pigny; Ivan Buckulcik, Ivo Wevers; Jan Hansen; Jose Antonio Ferreira Somoza; Leonel Marques Antunes Ferreira; Luca Gentini; Luigi Scibile; Kevin Buducan; Paolo Chiggiato; Stefano Sgobba; Purnalingam Revathi (UAntwerp); Roxane Misler; Emmanuel Berthome, Ana Teresa Pérez Fontenla
With the collaboration of Alexandre Lacroix (LAPP, Annecy)

## Slide 2: Introduction
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026
WP6.2 aims to write the final TDR for the ET vacuum pipe system. The ET vacuum pipes are 1-m diameter metallic tubes through which laser beams propagate in an ultrahigh vacuum (UHV) between the input and end mirrors of the interferometers. The length of such tubes is 120 km.
The objective is attained in steps of increasing complication :
        Design and laboratory study.
        Material and welding studies.
        Production and tests of smaller diameter prototypes
        Manufacturing, assembling, and testing a pilot sector.
The team includes CERN staff members contributing the equivalent of 2 FTEs, along with two CERN graduates. An engineer from the University of Antwerp joined the team in 2024. We are contractually linked to INFN, Nikhef, and IFAE, and maintain open collaboration with LAPP-CNRS (Annecy, FR) and parallel initiatives such as MacBeth (NL) and BeamPipes4ET (DE, BE, NL).
We report to the Engineering Department of the ET Organisation (ETO).
The WP6.2 is led by Paolo Chiggiato and Ana Teresa Perez Fontenla

## Slide 3: Outline
Work Overview
2025 & 2026 milestones
Ongoing developments
  Material & welding studies
  New support system design
  New vacuum components design
  New assembly strategies
Pilot Sector at CERN:
Work progress
Latest results
Next Steps
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 4: Timeline of our organizational work
2019
2020
2021
2022
2023
2024
2025
2026
2027
1st workshop at
LIGO Livingston
Framework collaboration
agreement
CERN-INFN-NIKHEF
Addendum on
CERN contribution to ET beampipes
Effective start of the technical activities
IFAE joins the collaboration agreement
Preliminary TDR
[ET-PP] including peer review
Start construction of the ET beampipe pilot sector
Extended TDR
ET-PP
2nd workshop at CERN
Review of the pilot sector design
Amendment signed by CERN, INFN, NIKHEF and IFAE
End of addendum and its amendment
Final TDR, including integration and fabrication drawings
Pilot sector operational
Test of different technical solutions with the pilot sector
3rd workshop at LIGO Hanford
4th workshop at CERN
CERN-NSF
Letter of Intent
CERN-NSF
Letter of Intent for collaboration in CE beamtube experiment (CEBEX)
Presentation to CERN management for approval of technical collaboration
ET-PP INFRA-DEV Kick-off Meeting
ET-ISB kick-off
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 5: Timeline of our technical work until end of 2025
Technical results and achievement presented at the October 2025 ET-PP review:
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 6: Timeline of our current technical work in 2026
Q1-2026
Q2-2026
Q3-2026
Q4-2026
1st beamline
pump-down
&
leak detection
Safety file for bakeout
Starting corrosion & toughness studies
Extended TDR ready
New beampipe support design completed
Starting bakeout
Reception of 1st tube SBE
ET-PP WP7 Workshop with industry at CERN
Accumulation measurements 1st beamline
Reception of SBE tubes completed
Reception of new bellows AISI 441
Technical results and achievements:
Start installation of 2nd beamline
Automated orbital weld tests completed
ET vacuum requirements tested on 1st beamline
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 7: The ET beam tube vacuum system TDR(s)
Q1 2025
Pre-TDR
Q2 2026
Extended TDR
ET beam tube
vacuum system
Extended TDR
Description of the system, materials, assembly, commissioning and risks identification
Detailed chapters, in-depth reports.
Logistics and sustainability further investigated.
Preliminary cost estimation.
Integration with civil engineering.
  Material and welding studies
  New support system design
  New vacuum components design
  New assembly strategies
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026
Ongoing developments:
Driven by previous work and pre-TDR review feedback

## Slide 8
Status & Results  Report under preparation
Preliminary study in collaboration with Universiteit Gent (B)
        Electrochemical testing in CETIM (FR)
      441and 444 show similar behavior than 304L
      No galvanic coupling risk
Material & Welding Studies: Corrosion Behavior
Objective: The study aims to compare the selected grades and welding processes used in the pilot sector against the baseline AISI 304L
Overlapping polarization curves confirm similar behavior
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026
Notes: “Are the materials electrochemically comparable?” → Yes — equivalent behavior, no galvanic risk

## Slide 9
Status & Results  Report under preparation
Preliminary study in collaboration with Universiteit Gent (B)
        Electrochemical testing in CETIM (FR)
      441and 444 show similar behavior than 304L
      No galvanic coupling risk
Material & Welding Studies: Corrosion Behavior
Immersion test in CETIM (FR)
  No general corrosion (3 months, severe conditions)
  Localized corrosion only (pitting / crevice) for all materials
  444 best overall performance (Mo effect)
  441 HAZ more sensitive in some welding configurations
Immersion results confirms that ferritic grades are suitable
Objective: The study aims to compare the selected grades and welding processes used in the pilot sector against the baseline AISI 304L
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026
9
Notes: “Do they perform under real conditions?
Yes — no general corrosion, with 444 showing the best performance

## Slide 10
Material & Welding Studies: Impact Resistance
Status & Results  Test campaign on-going
        Preliminary results: TIG autogenous AISI 441
        Currently under testing: TIG (with austenitic filler) & laser
        Fractography at CERN: on-going / next step
Objective: The study aims to evaluate the mechanical resistance of the Ferritic Stainless Steel AISI 441 using various welding methodologies (TIG, laser, plasma) with and without filler metal
Charpy V-notch impact test in Linde (DE)  ISO 9016
  HAZ (TIG autogenous)  reduced impact toughness
  Bake-out (150°C, 7 days)  no influence on behaviour
Base metal (G) | Weld metal (VWT) | Heat-affected zone (VHT)
HAZ is the limiting zone for impact resistance (preliminary)
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 11
Drawings courtesy of A. Lacroix (LAPP)
New support design in collaboration with LAPP
Status  Development on-going by LAPP-CNRS (FR)
        Lightweight and rigid support design
        Transfer function analysis completed
        Tunnel integration under evaluation
Objective: The study aims to improve support and alignment system design following pre-TDR feedback
High impact on performance — optimized for cost-effective design
Support concept
Integration in tunnel
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 12
Scheme courtesy of Romain Ganter (PSI)
New vacuum components design by SVAPET
Objective: Develop compact and reliable vacuum components for ET (flap valve, bellows, joints) to reduce both infrastructure costs and vacuum sector length
Status  Work on-going with Swiss industrial partners:
Stablished collaboration SVAPET (Swiss Vacuum & Precision – ET)
Led by PSI (Paul Scherrer Institute)
First flap valve prototype expected by early 2027
Key components for ET are under development with industry, with a clear path to industrialization
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 13
New baffle mounting scheme under discussion
The sketch showed above is not in scale and not representative of the final installation configuration.
New assembly strategy, including baffle integration
Objective: Assembly concepts are being redesigned to simplify installation and improve baffle alignment (in collaboration with IFAE)
Status  Work on-going
Current limitations
Risk of metal-to-metal contact  particle generation
High sensitivity to tube tolerances (shape & dimensions)
Design objectives
Minimize particle generation
Reduce installation time in tunnel
Simplify baffle integration & alignment
Ensure UHV compatibility & cleanability
Enable repairability
Move from complex on-site assembly to clean, pre-assembled solution
Possible joint design for 2nd beamline of the Pilot Sector
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 14
Pilot Sector: Validation Through Progressive Prototyping
Design & Requirements
Additional tests & Integration
Manufacturing Processes
Multiple design options were evaluated and refined
Each step validated a critical risk (buckling, weldability, dust control) before scaling to the ET Pilot Sector
Background system measurements were successfully completed mid-2025
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 15
Pilot Sector: Two-Line Integration Test Bench
Two-lines model to validate material, welding, assembly and full system integration
Installation under realistic constraints with ancillaries  reveals possible limitations
Identical pipe design and boundary conditions  controlled evaluation of improvements
Second line implements improvements  assembly, dust control, welding automation, baffles integration
Key numbers:
36 m pipeline of Ø1 m
Vacuum performance: H2 10-10 mbar
Cleanliness: ISO 6
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 16
Pilot Sector: Work Progress
Smooth pipes 4-mm thick reinforced by stiffeners on ferritic grade AISI 441
Ø1m x 6m sections from rolled & welded rings produced by pipe’s manufacturer (FR)
RT (10% of welds) by 3rd body, VT and metrological inspection (3D scan) by CERN
Tubes (6-m long) at their reception at TT4 (CERN)
1.5 m long rings
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 17
Smooth pipes 4-mm thick reinforced by stiffeners on ferritic grade AISI 441
Ø1m x 6m sections from rolled & welded rings produced by pipe’s manufacturer (FR)
RT (10% of welds) by 3rd body, VT and metrological inspection (3D scan) by CERN
Pre-cleaning of the components at CERN
Pre-cleaning
Pilot Sector: Work Progress
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 18
Smooth pipes 4-mm thick reinforced by stiffeners on ferritic grade AISI 441
Ø1m x 6m sections from rolled & welded rings produced by pipe’s manufacturer (FR)
RT (10% of welds) by 3rd body, VT and metrological inspection (3D scan) by CERN
Pre-cleaning of the components at CERN
Leak-tightness performed by CERN on 6-m long sections  all parts compliant for the 1st beamline
Fiducialisation of the parts
6 beam pipes: LR < 10-10 mbar l s-1
Pilot Sector: Work Progress
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 19
Smooth pipes 4-mm thick reinforced by stiffeners on ferritic grade AISI 441
Ø1m x 6m sections from rolled & welded rings produced by pipe’s manufacturer (FR)
RT (10% of welds) by 3rd body, VT and metrological inspection (3D scan) by CERN
Pre-cleaning of the components at CERN
Leak-tightness performed by CERN on 6-m long sections  all parts compliant for the 1st beamline
Fiducialisation of the parts
Cleaning dust-controlled packaging
Beam pipe packaged in ISO 6 conditions after degreasing
Pilot Sector: Work Progress
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 20
3 x 6 m tubes pre-alignment  Cleanroom installation for each joint  Protection removal  Sleeve installation  Manual welding  Installation on supports
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026
18-m array assembly completed
Pilot Sector: Work Progress

## Slide 21: 1st beamline bakeout completed
1st ET-PS beamline in position & leak tight  Electrical test (safety check implied 2 months delay but can be translated to ET)  Thermal insulation installation  Bakeout
Pilot Sector: Work Progress
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 22: 1st beamline vacuum commissioning completed
S: 6.1 l/s (H2O) during pumpdown and bakeout. S: 45.8 l/s (H2) after cooldown. Tamb: 23±2C
Successful bake out at 150°C for 7 days!
Pressure at room temperature is limited by the instrumentation’s outgassing rate
Data taking ongoing
Bakeout start
(150°C, 7days)
Instrumentation degassing
Cooldown
Pressure distribution between two ET pumping groups.
P pilot sector
Courtesy of Carlo Scarcia
Important milestone to validate the proposed technical solutions for ET
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026
Pilot Sector: Work Progress

## Slide 23: Outlook & Next Steps
Bellows in 441 manufacturing & testing
2nd line manufacturing and integration
Baffle integration optimization
New joining design validation
Integration of the new valve concept (SVAPET)
Cost estimation  contributing to ETO exercise
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026
2nd ET-PS beamline under manufacturing  Visit to company facilities in April 2026

## Slide 24: The ET beam tube vacuum system TDR(s)
Q1 2025
Pre-TDR
Q2 2026
Extended TDR
ET beam tube
vacuum system
Extended TDR
ET beam tube
vacuum system
Final TDR
Q4 2027
Final TDR
Description of the system, materials, assembly, commissioning and risks identification
Detailed chapters, in-depth reports.
Logistics and sustainability further investigated.
Preliminary cost estimation.
Integration with civil engineering.
Final version with optimal solutions.
Full integration with civil engineering
considering all the other services (HVAC, fire safety, …).
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 25
Thanks to the CERN team
and thank you for your attention!
1st ET-PS beamline installation in TT4 at CERN

## Slide 26
26
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 28: Background system
Paolo Chiggiato, ET beampipe activities at CERN, Barcelona, July 22nd, 2025
The leak detection was performed last week. No leak detected with a sensitivity better than 10-10 mbar l s-1.
This week the system is being prepared for bakeout. The first results are expected in 10 days: virtual leak rates, total gas loads (with and without pumps, instruments and valves).
QH2O = 3.4 10-10 mbar l s-1 cm-2
At 10 h of pumping
So far, so good!

## Slide 29: 1st beamline bakeout
1st ET-PS beamline in position & leak tight  Electrical test (safety check implied 2 months delay but can be translated to ET)  thermal insulation installation  bakeout
Pilot Sector: Work Progress
Anité Pérez, ET beampipe activities at CERN, Barcelona, May 5th, 2026

## Slide 30
Ferritic stainless steel in plate/coil format  max. width 1.5 m
Pipe production (external supplier)  Ø1 m x 6 m sections from rolled & welded rings (1.5 m each)
UHV validation  Leak-tightness performed by CERN on the 6-m long sections  all parts compliant for the 1st beamline
Manufacturing approach limits dimensional accuracy  cylindricity deviation ±6 mm meassured at the extremities making sleeve welding more complex and increasing particle generation
Pilot Sector: Industrial Constraints & Current Limitations
Industrial challenges:
→ Continuous manufacturing solutions → Improved tolerances
1.5 m long ring
6-m long section
Smooth pipes 4 mm thick reinforced by stiffeners

## Slide 31: ET-PS: leak detection
6 beam pipes:
LR < 10-10 mbar l s-1
1 beam pipe:
LR ~ 3×10-10 mbar l s-1
(≈ hundreds of nanometres defect)
The leak is located on a circumferential weld.
It seems to come from an overlapping weld bed.

## Slide 32: ET-PS: leak detection
Leak detection – NDT on leaking tube
PT: Some indication detected but probably fallacious due to superficial wrinkles.
RT: No indications.
Representative CS

## Slide 33
ET-PS: dust-controlled packing
Beam pipe packaged in ISO 6 conditions after degreasing.
Beam tube 4: Back packaged before front.
Excessive passages in front of HLF with extremity still exposed.
HLF: Horizontal Laminar Flow.
Packaging: 1) Protective film, 2) Plastic cap, 3) Protective film (outer layer)
Minimum five measurements (2’ duration each). Sampled volume: 100 L/side.

## Slide 34: ET-PS: 18 meter array assembly
Challenging installation.
50% of the joints were keeping ovalisation even with a rounding tooling installed.
Summary dust cleanliness during installation
After protection removal.
Only 0.3 μm particulate above limits.
The cause might be the storage.

## Slide 35: ET-PS: first beamline - electrical test (safety check)
Avg temperature measured along the chamber ~44°C
Highest temperature measured along the chamber ~54°C (central sleeve: 2 x 120 mm).
Temperature not stabilised, can be slightly higher in steady state.
V (3000 A) ~ 9 V
Schematic of the bakeout circuit.
Purpose: electrical connection on the beamline (from 0 to 3000 A)

## Slide 36
Full UHV manufacturing and testing at supplier
In-situ production in tunnel
Pipe sections (non-UHV) manufactured at industry
Sleeve
From pilot sector to full scale production
Scaling from 36m-long prototype to 120 km requires defining an industrial production and acceptance strategy
Complete fabrication + UHV validation at specialized facilities
Components delivered ready-to-install (UHV compliant)
Ensures high QC/QA
Challenging for logistics, transport constraints, sustainability, cost
Final transformation into UHV components near installation site (surface facilities and/or inside tunnel)
Reduced transport constraints (~15 m long sections)
More flexible industrialization
On-site controlled processes (cleanliness, welding, QC/QA)
Manufacturing + assembly directly in the tunnel
Minimizes transport, handling, logistics
Lower industrial maturity
Highest constraints (environment, QC/QA, cleanliness)

## Slide 37: Cleaning facility design and cost estimation
Cleaning facility to be built near the installation site to feed the front of the installation as it advances and reduce storage of conditioned tubes.
More information at: Surface finishing of the ET beam tube - Leonel Marques Antunes Ferreira (CERN)